## Product Catalog
Project Name | DealMart
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website. (DealMart_Epic_001) | US001 | First time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can see the product I buy. | New
| US002 | New user can register on the website | As a first-time visitor to the e-commerce website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | New
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website. So that I can make my choice and buy a listed product from the website. | New
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed product from the website. | New
| US005 | Registered User can make payment for the items added to the cart. | As a Registered Website User, I want to be able to buy listed products. So that I can use the product I buy. | New

## Sprint Planning
Project Name | DealMart
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can se the product I buy. | 8 | 1
| US002 | New user can register on the website | As a first-time visitor to the e-commerce website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | 3 | 1
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website. So that I can make my choice and buy a listed product from the website. | 5 | 2
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed product from the website. | 5 | 3
| US005 | Registered User can make payment for the items added to the cart. | As a Registered Website User, I want to be able to buy listed products. So that I can use the product I buy. | 8 | 3

## Sheet1
TestCaseID | UserStoryID | Feature | User Story | Steps | Execpted Result
TC_DL_001 | US001 | First time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can see the product I buy. | 1) Open Application URL 2) Go to Catalog Page 3) List a product 4) Add to Cart 5) Select Payment Method 6)Complete Payment | User is able to list and buy the product
TC_DL_002 | US002 | New user can register on the website | As a first-time visitor to the e-commerce website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | 1) Open Application URL 2) Click on Registered Link 3) Update User Details 4) Click on Submit | New user should be able to register on site.

## Tasks
QA Tasks | Developer Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test Cases | Setting up Development Environment
Setting up Test Environment | Developing Programs
Creating Test Data | Code Review
Executing Manual Tests | Creating Unit Test Cases
Automation Setup | Executing Unt Tests
Automation Design | Merging Code
Automating Test Cases | Creating Builds
Re-Testing Bugs | Fixing Bugs
Regression Testing
Demo User Story